## rest_features_estimation (2)
Main Module | Sub_modules
PINs | 1. Search PIN 2. Search PIN Batch 3. Search Reseller Connected PINs 4. Search Device Wise Reseller PINs 5. Search PIN Return Request
Reseller | 1. Search Reseller Client 2. Search All Reseller List
IP-Management | 1. Search IP List 2. Search Ip Bundle List 3. Search PIN Batch (IP) 4. Search Server Lock Schedule List 5. Search Country With IP Bundle
Reseller Panels | 1. Search Resellers Customized Panel List
VPN Server | 1. Search VPN Server List 2. Server Live Monitoring
Push Management | 1. Search Applications List 2. Search Push Automation List 3. Search Pending Push Request 4. Search User List For Push 5. Search Push Template 6. Search Notice List 7. Ad New Image 8. Ad Banner Image List for TESTING 9. Search Ad Banner Image List 10. Apps Dynamic Menu Management
Campaign | 1. Search Campaign List 2. Search Affiliator Client 3. Search Affiliate Withdraw TNX 4. Search Affiliator Payment Gateways 5. Search Affiliator Sign Up Requests 6. Search Website Form Request 7. Search VPN Offer Sliders | p
Rate Section | 1. Search Rate Plan 2. Edit Subscription Plan
Referrals | 1. Search Referral Bonus Transaction Report 2. Search premium validity for free users 3. Search referral code user list
Application | 1. Application & Variable Settings 2. Search Admin Panel List 3. search signup blacklist domain 4. Edit domain Information 5. Search App CRC Block List
Purchase management | 1. edit payment method 2. Search purchase attempt logs
User & Permission | 1. Update admin 2. Search Role List 3. edit role 4. Search Role User List 5. Search Role Menu Permission List 6. Search User Menu Permission List
Subscription Code | done
Report Online Pins |  |  | 3-4days
Reseller report online pin |  |  | 1
Report Online Pins |  |  | 2
Report log |  |  | 1
Server connection |  |  | 2
Payment and recharge |  |  | 1
Email report |  |  | 1
Reseller report |  |  | 1
SSL com
TOTAL : 30 Days

## rest_features_estimation
Main Module | Sub_modules
PINs | 1. Search PIN 2. Search PIN Batch 3. Search Reseller Connected PINs 4. Search Device Wise Reseller PINs 5. Search PIN Return Request |  | 1 day
Reseller | 1. Search Reseller Client 2. Search All Reseller List |  | half day
IP-Management | 1. Search IP List 2. Search Ip Bundle List 3. Search PIN Batch (IP) 4. Add Server Lock Schedule List 5. Edit Server Lock Schedule List 6. Search Server Lock Schedule List 7. Search Country With IP Bundle | add + edi form = 1 day search =1 | 2days
Reseller Panels | 1. Search Resellers Customized Panel List 2. New Customize Reseller Panel |  | 1
VPN Server | 1. Search VPN Server List 2. Server Live Monitoring
Push Management | 1. Edit APP 2. Search Applications List 3. Search Push Automation List 4. Edit Push Automation 5. Search Pending Push Request 6. Search User List For Push 7. Edit Push Template 8. Search Push Template 9. Search Notice List 10. Edit Notice 11. Edit Banner 12. Ad New Image 13. Ad Banner Image List for TESTING 14. Search Ad Banner Image List 15. Apps Dynamic Menu Management | add form = 1 day edit form = 1 search= 1 | 3 days
Campaign | 1. Search Campaign List 2. Search Affiliator Client 3. Edit Reseller Client 4. Search Affiliate Withdraw TNX 5. Search Affiliator Payment Gateways 6. Edit Payment Gateway 7. Search Affiliator Sign Up Requests 8. Search Website Form Requests 9. Edit Request (servers) 10. Edit Request (right_for_us) 11. Edit Request Student Ambassador Request 12. Add New Offer Banners Rule 13. Search VPN Offer Sliders | form = 2 search =1 | 3 days
Rate Section | 1. Search Rate Plan 2. Edit Subscription Plan |  | 1.5 days
Referrals | 1. Search Referral Bonus Transaction Report 2. Search premium validity for free users 3. Search referral code user list
Application | 1. Application & Variable Settings 2. Add new admin panel 3. Search Admin Panel List 4. search signup blacklist domain 5. Edit domain Information 6. Search App CRC Block List 7. Edit app CRC |  | 2 days
Purchase management | 1. edit payment method 2. Search purchase attempt logs |  | 3 days
User & Permission | 1. Update admin 2. Search Role List 3. edit role 4. Search Role User List 5. Search Role Menu Permission List 6. Search User Menu Permission List
Subscription Code | 1. Search PIN 2. Add new pin batch (code generation)
Report Online Pins |  |  | 3-4days
Reseller report online pin |  |  | 1
Report Online Pins |  |  | 2
Report log |  |  | 1
Server connection |  |  | 2
Payment and recharge |  |  | 1
Email report |  |  | 1
Reseller report |  |  | 1
SSL com
TOTAL : 30 Days

## Sheet1
Sub_modules
1. Search PIN
2. Search PIN Batch | Day 1 | Search PIN
3. Search Reseller Connected PINs |  | Search PIN Batch
4. Search Device Wise Reseller PINs
5. Search PIN Return Request | Day 2 | Search Reseller Connected PINs
6. Search Reseller Client |  | Search Device Wise Reseller PINs
7. Search All Reseller List
8. Search IP List | Day 3 | Search PIN Return Request
9. Search Ip Bundle List |  | Search Reseller Client
10. Search PIN Batch (IP)
11. Search Server Lock Schedule List | Day 4 | Search All Reseller List
12. Search Country With IP Bundle |  | Search IP List
13 . Search Resellers Customized Panel List
14.Search VPN Server List | Day 5 | Search Ip Bundle List
15. Server Live Monitoring |  | Search PIN Batch (IP)
16.Search Applications List
17. Search Push Automation List | Day 6 | Search Server Lock Schedule List
18. Search Pending Push Request |  | Search Country With IP Bundle
19. Search User List For Push
20. Search Push Template | Day 7 | Search Resellers Customized Panel List
21/ Search Notice List |  | Search VPN Server List
22 Ad Banner Image List for TESTING
23. Search Ad Banner Image List | Day 8 | 15. Server Live Monitoring
24. Search Rate Plan |  | 16.Search Applications List
25.Search Referral Bonus Transaction Report
26. Search premium validity for free user | Day 9 | 17. Search Push Automation List
27. Search referral code user list |  | 18. Search Pending Push Request
28. Search Admin Panel List
29.search signup blacklist domain | Day 10 | 19. Search User List For Push
30. Search App CRC Block List |  | 20. Search Push Template
31. Search Role List
32. Search Role Menu Permission List | Day 11 | 21/ Search Notice List
22 Ad Banner Image List for TESTING
| Day12 | 23. Search Ad Banner Image List
24. Search Rate Plan
| Day 13 | 25.Search Referral Bonus Transaction Report
26. Search premium validity for free user
| Day14 | 27. Search referral code user list
28. Search Admin Panel List
| Day15 | 29.search signup blacklist domain
30. Search App CRC Block List
| Day 16 | 31. Search Role List
32. Search Role Menu Permission List