## rest_ features_estimation
Main Module | Sub_modules
PINs | 1. Search PIN 2. Search PIN Batch 3. Search Reseller Connected PINs 4. Search Device Wise Reseller PINs 5. Search PIN Return Request |  | 1 day
Reseller | 1. Search Reseller Client 2. Search All Reseller List |  | half day
IP-Management | 1. Search IP List 2. Search Ip Bundle List 3. Search PIN Batch (IP) 4. Add Server Lock Schedule List 5. Edit Server Lock Schedule List 6. Search Server Lock Schedule List 7. Search Country With IP Bundle | add + edi form = 1 day search =1 | 2days
Reseller Panels | 1. Search Resellers Customized Panel List 2. New Customize Reseller Panel |  | 1
VPN Server | 1. Search VPN Server List 2. Server Live Monitoring
Push Management | 1. Edit APP 2. Search Applications List 3. Search Push Automation List 4. Edit Push Automation 5. Search Pending Push Request 6. Search User List For Push 7. Edit Push Template 8. Search Push Template 9. Search Notice List 10. Edit Notice 11. Edit Banner 12. Ad New Image 13. Ad Banner Image List for TESTING 14. Search Ad Banner Image List 15. Apps Dynamic Menu Management | add form = 1 day edit form = 1 search= 1 | 3 days
Campaign | 1. Search Campaign List 2. Search Affiliator Client 3. Edit Reseller Client 4. Search Affiliate Withdraw TNX 5. Search Affiliator Payment Gateways 6. Edit Payment Gateway 7. Search Affiliator Sign Up Requests 8. Search Website Form Requests 9. Edit Request (servers) 10. Edit Request (right_for_us) 11. Edit Request Student Ambassador Request 12. Add New Offer Banners Rule 13. Search VPN Offer Sliders | form = 2 search =1 | 3 days
Rate Section | 1. Search Rate Plan 2. Edit Subscription Plan |  | 1.5 days
Referrals | 1. Search Referral Bonus Transaction Report 2. Search premium validity for free users 3. Search referral code user list
Application | 1. Application & Variable Settings 2. Add new admin panel 3. Search Admin Panel List 4. search signup blacklist domain 5. Edit domain Information 6. Search App CRC Block List 7. Edit app CRC |  | 2 days
Purchase management | 1. edit payment method 2. Search purchase attempt logs |  | 3 days
User & Permission | 1. Update admin 2. Search Role List 3. edit role 4. Search Role User List 5. Search Role Menu Permission List 6. Search User Menu Permission List
Subscription Code | 1. Search PIN 2. Add new pin batch (code generation)
Report Online Pins |  |  | 3-4days
Reseller report online pin |  |  | 1
Report Online Pins |  |  | 2
Report log |  |  | 1
Server connection |  |  | 2
Payment and recharge |  |  | 1
Email report |  |  | 1
Reseller report |  |  | 1
SSL com
TOTAL : 30 Days